## Data (hidden)
Edu-Syria Expense
Project costs categories relating to workplan |  |  |  | Budget and Expenses
Cost Category |  | Description |  | Total budget (grant + co-funding) | Quarter 1 |  |  |  | Quarter 2 |  |  |  | Quarter 3 |  |  |  | Total
[5 empty] | Budget | Expenses | Deviation absolute | Deviation in % | Budget | Expenses | Deviation absolute | Deviation in % | Budget | Expenses | Deviation absolute | Deviation in % | Realised expenses | Budgetted expenses | Deviation absolute | Deviation in %
a |  | Cost of staff assigned to the project |  | 26503.4634 | 8835 | 5663.19 | -3171.81 | -35.9% | 12007 | 10290.8107 | -1716.1893 | -14.29% | 8835 | 10165.74 | 1330.74 | 15.06% | 26119.7407 | 26503.4634 | 383.7227 | 98.55%
b |  | Travel and subsistence costs for staff and other persons taking part in the project |  | 8802.4788 | 4801 | 0 | -4801 | -100% | 6241 | 2272.8001 | -3968.1999 | -63.58% | 2560 | 6999.29 | 4439.29 | 173.4% | 9272.0901 | 8802.4788 | -469.6113 | 105.3%
c |  | Costs of consumables |  | 768.2163 | 0 | 0 | 0 | 0% | 768 | 492.3839 | -275.6161 | -35.89% |  |  | 0 | 0% | 492.3839 | 768.2163 | 275.8325 | 64.09%
d |  | Costs of service, supply and work contracts awarded by the requesting organisation |  | 23926.0976 | 840 | 0 | -840 | -100% | 15284 | 1246.3084 | -14037.6916 | -91.85% | 8642 | 20403.9 | 11761.9 | 136.1% | 21650.2084 | 23926.0976 | 2275.8892 | 90.49%
|  | Total grant |  | 60000.2561 | 14476 | 5663.19 | -8812.81 | -60.88% | 34300 | 14302.3031 | -19997.6969 | -58.3% | 20037 | 37568.93 | 17531.93 | 87.5% | 57534.4231 | 60000.2561 | 2465.833
g |  | Co-Funding |  | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0%
Total budget |  |  |  | 60000.2561 | 14476 | 5663.19 | -8812.81 | -60.88% | 34300 | 14302.3031 | -19997.6969 | -58.3% | 20037 | 37568.93 | 17531.93 | 87.5% | 57534.4231 | 60000.2561 | 2465.833 | 95.89%
Vouch | Date | Description |  | Amount $ | Amount JOD | Payment date | Currency Rate | Amount EUR Based on Actual Rates | Orginal Amount EUR Rate (0.78103) |  | Budget Lines | [9 empty] | 0.15891 | 19965.4931 | fiiled Q1 |  | 3559.5905 | 2765.6512
[11 empty] | A. Costs of staff | B. Travel and subsistence costs | C. Purchase costs for equipment | D. Costs of consumables | E. Costs entailed by contracts | F. Costs from contract req. | G. Co-funding | [8 empty] | 1688.68
NO-001 | 21-06-17 | Service agreement for 24May-23June 2021 -Hala al-ma'aitah |  | 2118.64 | 1499.9971 | 21-06-28 | 0.84612 | 1772.7948 | [12 empty] | 19965.4931 |  | 3559.5905 |  | 19965.4931 | 133.43
NO-002 | 21-06-29 | Service agreement for 24June-23 July 2021 -Hala al-ma'aitah |  | 2118.64 | 1499.9971 | 21-07-08 | 0.83949 | 1786.7957
NO-003 | 21-07-05 | Admin cost | [19 empty] | DIFF |  | -2765.6512
|  | Project coordinator |  | 2010.06 | 1423.1225 | several rates |  | 1679.38 | [12 empty] | 1679.38 |  | 1679.38 |  | 1679.3827
|  | Account & administration |  | 0 | 0 |  |  | 0 | [14 empty] | 1679.3827
|  | Q1 TOTAL |  | 6247.34 |  |  |  | 5238.9705 | 5663.18 | [13 empty] | 0.0026848 |  | 1679.38
NO-004 | 21-08-31 | Exchage rate for vouchers 1 to 3 |  | 0 |  |  |  |  | -424.2095
NO-005 | 21-08-24 | Service agreement for 24 July-23 Aug 2021 -Hala al-ma'aitah |  | 2118.64 | 1499.9971 | 21-08-18 | 0.83272 | 1801.3223 | 1801.32 | [11 empty] | Details of satff for Q2:
NO-006 | 21-10-14 | Service agreement for 24 Aug-23 sep 2021 -Hala al-maaita |  | 2118.64 | 1499.9971 | 21-10-14 | 0.82186 | 1825.1249 | 1825.12 | [11 empty] | Hala | 7056.04 | [6 empty] | Amount (EUR)
NO-007 | 21-10-17 | Advance to Hala |  | 282.49 | 200.0029 | 21-10-17 | 0.82253 | 0 | [12 empty] | Helen | 3122.98
NO-008 | 21-11-04 | Transportation |  | 1306.5 | 925.002 | 21-11-04 | 0.81845 | 1130.1875 | 1130.19 | [11 empty] | Danah | 83.04 | [5 empty] | Transportation | 0
NO-009 | 21-11-11 | Service agreement for 24 sep- 25 October 2021 -Hala al-ma'aitah |  | 2118.64 | 1499.9971 | 21-11-11 | 0.81285 | 1845.3554 | 1845.36 | [11 empty] | Saja | 28.76 | [5 empty] | Training room rental fees | 0
NO-010 | 21-11-15 | Transportation 7-18 Nov 2021 |  | 1306.5 | 925.002 | 21-11-15 | 0.80955 | 1142.6126 | 1142.61 | [18 empty] | Training Expense | 0
NO-011 | 21-11-17 | Training room rental fees invoice covering 20 days at AMRTC |  | 1412.43 | 1000.0004 | 21-11-17 | 0.80237 | 1246.3084 | 1246.31 | [13 empty] | 8.714% |  |  |  |  | Project Stationery and Supplies | 0
NO-012 | 21-11-22 | Return Advance Payment |  | -282.49 | -200.0029 | 21-11-22 | 0.79988 | 0 | [12 empty] | Total | 10290.82
NO-013 | 21-11-22 | Project Stationery and Office Supplies |  | 238.21 | 168.656 | 21-10-21 | 0.82542 | 204.3275 | 204.33 | [18 empty] | Total | 0
|  | Project Stationery |  | 115.53 | 81.793 | 21-11-18 | 0.8052 | 101.581 | 101.58 | [13 empty] | 2.139%
|  | Training Supplies |  | 212.08 | 150.15 | 21-11-18 | 0.8052 | 186.4754 | 186.48 | [13 empty] | 1.304%
NO-013/01 | 21-11-24 | Services Agreement for Oct 24th - Nov 23th, 2021 |  | 2118.64 | 1499.9971 | 21-11-24 | 0.80397 | 1865.7277 | 1865.73
NO-014 | 21-11-24 | Admin cost | [18 empty] | Details below is the adjustment:
|  | Project coordinator |  | 3896.41 |  |  |  | 3377.49 | 3377.49 | [11 empty] | EURO
|  | Account & administration | [22 empty] | Should filled | sent
|  | Q2 TOTAL |  | 16962.22 |  |  |  | 14726.5126 | 14302.3105 | [11 empty] | Helen | 502.4149 | 691.2859 | 361.5786 | 1555.2795 | 1688.68 | -133.4
|  | Total |  | 23209.56 |  |  |  | 19965.4831 | 19965.48 | [11 empty] | Dana | 0 | 60.6534 | 63.4498 | 124.1032 | 133.43 | -9.32
NO-015 | 21-12-01 | Third Phase Transportation allowance |  | 2016.95 | 1428.0006 | 21-12-05 | 0.80296 | 1778.41 | 1778.4106 |  |  | 1778.41 | [8 empty] | Total | 502.4149 | 751.9394 | 425.0284 | 1679.3827 |  | -142.72
NO-016 | 21-12-20 | Services Agreement for Nov 24th - Dec 25th, 2021 |  | 2118.64 | 1499.9971 | 21-12-20 | 0.79772 | 1880.35 | 1880.3454 |  | 1880.35
NO-017 | 21-12-20 | Offset amount between Advance Payment & Actual expenduries Plus Transportation In Vouchers No.7 & 13 & 10 |  | 0 | 0 | 21-12-20 | 0.79772 | 0 | [12 empty] | Hala |  |  |  | 3559.59 | 3841.08 | -281.49
NO-018 | 21-12-20 | Third Phase Transportation allowance 13 - 26/Dec |  | 1200.56 | 849.9965 | 21-12-20 | 0.79772 | 1065.53 | 1065.5324 |  |  | 1065.53
| 21-12-20 | Return Back from Voucher No.0010 |  | -88.98 | -62.9978 | 21-12-20 | 0.79772 | -78.97 | -78.9724 |  |  | -78.97
NO-019 | 21-12-22 | Settlement Invoice No. INV112078 dated on Dec 20th covering 40 Hours English Communication Skills course - As Per the attached agreement. |  | 5014.12 | 3549.997 | 21-12-22 | 0.79996 | 4437.73 | 4437.7347 | [5 empty] | 4437.73
NO-020 | 21-12-22 | Purchase Laptops from Center of Excellence with Qty.17 |  | 12245.76 | 8669.9981 | 21-12-22 | 0.79999 | 10837.62 | 10837.6195 | [5 empty] | 10837.62 | [11 empty] | -424.21
NO-022 | 21-12-30 | Adjust Ahmad's work effort for Dec.2021 - Salary |  | 464.14 | 328.611 | 21-12-30 | 0.80231 | 409.58 | 409.5806 |  | 409.58
NO.022 | 21-12-30 | Adjust Ahmad's work effort for Dec.2021 - Social Security |  | 66.14 | 46.83 | 21-12-30 | 0.80231 | 58.37 | 58.3689 |  | 58.37
NO-025 | 21-12-30 | Admin cost
|  | Project coordinator - Salary |  | 690.48 | 488.86 | 21-12-30 | 0.879 | 606.93 | 606.9319 |  | 606.93
|  | Project coordinator - Social Security |  | 52.82 | 37.34 | 21-12-30 | 0.879 | 46.43 | 46.4288 |  | 46.43
|  | Project coordinator - Retirement |  | 2.65 | 1.87 | 21-12-30 | 0.879 | 2.33 | 2.3293 |  | 2.33
|  | Account - Salary |  | 221.01 | 156.48 | 21-12-30 | 0.879 | 194.27 | 194.2678 |  | 194.27
|  | Account - Social Security |  | 31.49 | 22.29 | 21-12-30 | 0.879 | 27.68 | 27.6797 |  | 27.68
|  | Administration - Salary |  | 34.05 | 24.11 | 21-12-30 | 0.879 | 29.93 | 29.9299 |  | 29.93
|  | Administration - Social Security |  | 4.85 | 3.43 | 21-12-30 | 0.879 | 4.26 | 4.2631 |  | 4.26
NO-021 | 22-01-11 | Third Phase Transportation allowance 08 - 27/Jan |  | 1200.57 | 850 | 22-01-11 | 0.80465 | 1056.37 | 1056.3652 |  |  | 1056.37
| 22-01-11 | Adjust Voucher No.18 |  | -21.19 | -15 | 22-01-11 | 0.80465 | -18.64 | -18.6417 |  |  | -18.64
NO-021/01 | 22-01-02 | Account - Salary |  | 464.14 | 328.61 | 21-12-30 | 0.879 | 407.98 | 407.9791 |  | 407.98
|  | Account - Social Security |  | 66.14 | 46.83 | 21-12-30 | 0.879 | 58.14 | 58.1371 |  | 58.14
NO-023 | 22-01-20 | Third Phase Transportation allowance 10 - 22/Jan |  | 1200.57 | 850 | 22-01-20 | 0.80472 | 1056.26 | 1056.2628 |  |  | 1056.26
|  | Adjust Voucher No.21 |  | -56.5 | -40 | 22-01-20 | 0.80472 | -49.71 | -49.7065 |  |  | -49.71
NO-024 | 22-01-23 | Services Agreement for Dec 24th,2021 - Jan 23rd, 2022 |  | 2118.64 | 1500 | 22-01-23 | 0.80487 | 1863.66 | 1863.655 |  | 1863.66
NO-024/01 | 22-01-23 | Bank Charges |  | 0.71 | 0.5 | 22-01-23 | 0.80487 | 0.62 | 0.62122 |  | 0.62
NO-024/02 | 22-01-31 | Admin cost
|  | Project coordinator - Salary |  | 644.84 | 456.55 | 22-01-31 | 0.89218 | 575.31 | 575.3114 |  | 575.31
|  | Project coordinator - Social Security |  | 49.33 | 34.93 | 22-01-31 | 0.89218 | 44.01 | 44.0111 |  | 44.01
|  | Project coordinator - Retirement |  | 32.24 | 22.83 | 22-01-31 | 0.89218 | 28.76 | 28.7638 |  | 28.76
|  | Account - Salary |  | 1519.06 | 2145.56 | 22-01-31 | 0.89218 | 1355.27 | 1355.2704 |  | 1355.27
|  | Account - Social Security |  | 216.46 | 305.73 | 22-01-31 | 0.89218 | 193.12 | 193.1206 |  | 193.12
|  | Administration - Salary |  | 20.05 | 28.32 | 22-01-31 | 0.89218 | 17.89 | 17.8881 |  | 17.89
|  | Administration - Social Security |  | 2.86 | 4.04 | 22-01-31 | 0.89218 | 2.55 | 2.5516 |  | 2.55
NO-026 | 22-02-01 | Invoice No. 07/2022 dated on Jan 31,2022 Covering Graphic Design Specialist Training. |  | 5649.72 | 4000 | 22-02-01 | 0.79914 | 5005.38 | 5005.3808 | [5 empty] | 5005.38
NO-027 | 22-02-06 | 3 Hours Rental fees for the Vedio Session |  | 141.24 | 100 | 22-02-06 | 0.81186 | 123.17 | 123.1739 | [5 empty] | 123.17
NO-028 | 22-02-10 | Third Phase Transportation allowance 23 Jan - 22/Feb |  | 108.76 | 77 | 22-02-10 | 0.81062 | 94.99 | 94.989 |  |  | 94.99
NO-029 | 22-02-16 | Third Phase Transportation allowance |  | 2387.01 | 1690 | 22-02-16 | 0.80666 | 2095.05 | 2095.0482 |  |  | 2095.05
NO-030 | 22-02-15 | Admin cost
|  | Project coordinator - Salary |  | 520.83 | 368.75 | 22-02-15 | 0.87997 | 458.31 | 458.3148 |  | 458.31
|  | Project coordinator - Social Security |  | 39.84 | 28.21 | 22-02-15 | 0.87997 | 35.06 | 35.058 |  | 35.06
|  | Project coordinator - Retirement |  | 26.04 | 18.44 | 22-02-15 | 0.87997 | 22.91 | 22.9144 |  | 22.91
|  | Account - Salary |  | 401.26 | 284.09 | 22-02-15 | 0.87997 | 353.1 | 353.0968 |  | 353.1
|  | Account - Social Security |  | 57.19 | 40.49 | 22-02-15 | 0.87997 | 50.33 | 50.3255 |  | 50.33
|  | Administration - Salary |  | 7.66 | 5.42 | 22-02-15 | 0.87997 | 6.74 | 6.7406 |  | 6.74
|  | Administration - Social Security |  | 1.09 | 0.77 | 22-02-15 | 0.87997 | 0.96 | 0.95917 |  | 0.96
NO-031 | 22-02-23 | Advance Payment to Hala for (Office stationery and supplies for the training / Stationery and office supplies for training/graduation supplies / certificates). | 360.17 |  | 0 | 22-02-23 | 0.80432 | 0 | 0
|  | Extra Amount Paid from Hala to The internet Cards | 35.93 |  | 0 | 22-02-23 | 0.80432 | 0 | 0
|  | Less: Remining amount Voucher No.29 | -91.81 |  | 0 | 22-02-23 | 0.80432 | 0 | 0
NO-032 | 22-02-24 | Services Agreement for Jan 24th - Feb 24th,2022 |  | 2118.64 | 1500 | 22-02-24 | 0.79046 | 1897.63 | 1897.634 |  | 1897.63
NO-033 | 22-03-31 | Admin cost Covering Period from Feb 16 - 28.2022:
|  | Project coordinator - Salary |  | 331.44 | 234.66 | 22-03-31 | 0.90126 | 298.71 | 298.712 |  | 298.71
|  | Project coordinator - Social Security |  | 25.36 | 17.95 | 22-03-31 | 0.90126 | 22.86 | 22.8558 |  | 22.86
|  | Project coordinator - Retirement |  | 16.57 | 11.73 | 22-03-31 | 0.90126 | 14.93 | 14.9338 |  | 14.93
|  | Account - Salary |  | 215.44 | 152.53 | 22-03-31 | 0.90126 | 194.17 | 194.1664 |  | 194.17
|  | Account - Social Security |  | 30.7 | 21.74 | 22-03-31 | 0.90126 | 27.67 | 27.6685 |  | 27.67
|  | Administration - Salary |  | 15.31 | 10.84 | 22-03-31 | 0.90126 | 13.8 | 13.7982 |  | 13.8
|  | Administration - Social Security |  | 2.18 | 1.54 | 22-03-31 | 0.90126 | 1.96 | 1.9647 |  | 1.96
|  | Admin cost Covering Period Mar 01 - 31.2022: | [8 empty] | 0
NO-034 | 22-03-31 | Project coordinator - Salary |  | 608.7 | 430.9596 | 22-03-31 | 0.90126 | 548.59 | 548.5939 |  | 548.59
|  | Project coordinator - Social Security |  | 46.57 | 32.9716 | 22-03-31 | 0.90126 | 41.97 | 41.9714 |  | 41.97
|  | Project coordinator - Retirement |  | 30.43 | 21.5444 | 22-03-31 | 0.90126 | 27.43 | 27.4252 |  | 27.43
|  | Account - Salary |  | 201.78 | 142.8602 | 22-03-31 | 0.90126 | 181.86 | 181.8552 |  | 181.86
|  | Account - Social Security |  | 28.76 | 20.3621 | 22-03-31 | 0.90126 | 25.92 | 25.94 |  | 25.92
NO-034/01 | 22-04-01 | Advance Payment to Hala for (Office stationery and supplies for the training / Stationery and office supplies for training/graduation supplies / certificates). |  | 360.17 | 255.0004 | 22-04-01 | 0.90551 | 326.14 | 326.1379 |  |  |  |  | 326.14
|  | Extra Amount for internet Cards |  | 35.93 | 25.4384 | 22-04-01 | 0.90551 | 32.54 | 32.535 |  |  | 32.54
|  | Less: Remining amount Voucher No.29 |  | -91.81 | -65.0015 | 22-04-01 | 0.90551 | -83.13 | -83.135 |  |  | -83.13
NO-035 | 22-04-30 | Return Back from Voucher No.0029 with RV No.20608 |  | -247.18 | -175 | 22-04-30 | 0.94843 | -234.43 | -234.4329 |  |  | -234.43
NO-036 | 22-04-30 | Project coordinator - Salary |  | 729.17 | 516.25 | 22-04-30 | 0.94843 | 691.57 | 691.5667 |  | 691.57
|  | Project coordinator - Social Security |  | 55.78 | 39.49 | 22-04-30 | 0.94843 | 52.9 | 52.9034 |  | 52.9
|  | Project coordinator - Retirement |  | 36.46 | 25.81 | 22-04-30 | 0.94843 | 34.58 | 34.5798 |  | 34.58
NO-037 | 22-05-18 | PEGASUS Invoice No.1014 dated May 16th,2022 Covering the Promotional Subtitle Video Fees |  | 141.24 | 100 | 22-05-18 | 0.95175 | 134.43 | 134.4252 |  |  |  |  | 134.43
NO-038 | 22-05-18 | Less: Project coordinator - Salary |  | -374.96 | -265.47 | 22-04-30 | 0.94843 | -355.62 | -355.6233 |  | -355.62
[11 empty] | 12455.78 | 6714.27 | 0 | 460.57 | 20403.9 | 0 | 0
|  | Q4 TOTAL |  | 45189.92 | 33233.0876 |  |  | 40034.52 | 40034.5167
|  |  |  | 68399.48 |  |  |  | 60000.0031 | 59999.9967 |  | 1823.3 | -285.02 | 0 | 460.57 | 0 | 0 | 0

## Budget explanation
EDU-Syria budget proposal |  |  | Budget
1
Budget explanation
Costs breakdown
Cost category | Description | Eligbile costs
a | Cost of staff assigned to the project | Salaries - Costs budgeted under this Budget Heading may be used for payment of salaries and fees of the project staff contracted by the Implementing Organisation or its Partner(s). Subcontracted services (payments to companies under service contracts) cannot be claimed under this Budget Heading. - Salaries and costs should not exceed those normally borne by the Implementing Organisation or its Partner(s). - Cost of staff assigned must include actual salaries plus social security charges and other remuneration-related costs (excluding performance-based bonuses).
b | Travel and subsistence costs for staff and other persons taking part in the project | Cost budgeted under this Budget Heading are used to cover: International travel/transportation expenditures of project staff and other person taking part in the project from/to the implementation place of the Action for the needs/activities of the Project. Local transportation sub-heading is used to cover intercity transport expenditures within the country of implementation Subsistence cost/Per diems - Per diems under this Budget Line are allowed for the project staff and other person taking part in the project and can also be used for the conference, seminar etc. participants in case their meal, accommodation and other costs are not covered under other Budget Lines. - Per diems cover all meal, inner city travel and hotel expenses, and are calculated on overnight basis. - Costs should not exceed those normally borne by the Implementing Organisation or its Partner(s). - Per diems should not be higher than the EU maximum rates published on: https://ec.europa.eu/international-partnerships/system/files/per-diem-rates-20200201_en.pdf
c | Purchase costs for equipment (new or used) and supplies | The purchase of equipment and supplies are eligible provided they are included in the budget and correspond to market rates. The Implementing Organisation is obliged to obtain value for money, and to use the tendering procedures in accordance with the principles of transparency, competition and equal treatment.
d | Costs of consumables | Cost of stationary, office materials, photocopies, etc. for the needs of the implementation of project activities.
e | Costs of service, supply and work contracts awarded by the requesting organisation | This budget heading is for the costs that will be fully sub-contracted services such as publications, organisation of events.
f | Costs deriving directly from the requirements of the contract | Dissemination of information, evaluation specific to the project, audits, translation, reproduction, insurance, etc. including financial service costs (in particular the cost of transfers and financial guarantees where required according to the Contract). Please note that only certified translations are accepted.
g | Co-funding
Applicants are requested to submit their budgets in EUR

## EDU-Syria budget proposal
EDU-Syria budget proposal | [33 empty] | Budget
1
General Project information |  | Project name: | [31 empty] | 2
|  | Project number: |  |  | < enter project nr. > | [28 empty] | 3
|  | Applying organization: | [31 empty] | 4
|  | Grant amount: | [31 empty] | 5
|  | Project period: |  |  |  |  | - | [26 empty] | 6
|  | Project duration (months) | [31 empty] | 0
Reporting quarter
Summary per Outcome
Project Outcomes relating to workplan |  |  |  |  | Budget and Expenses
Outcome |  | Description | #Unit | Cost per unit | Total budget (grant + co-funding) | Reallocation
Justification
Outcome 1 < Insert title > | a | Cost of staff assigned to the project |  |  | 0 |  | Q1 | 0
| b | Travel and subsistence costs for staff and other persons taking part in the project |  |  | 0 |  |  | 0
| c | Purchase costs for equipment (new or used) and supplies |  |  | 0 |  |  | 0
| d | Costs of consumables |  |  | 0 |  |  | 0
| e | Costs of service, supply and work contracts awarded by the requesting organisation |  |  | 0 |  |  | 0
| f | Costs deriving directly from the requirements of the contract |  |  | 0 |  |  | 0
| g | Co-Funding |  |  | 0 |  |  | 0
|  | (Sub)Outcome total | 0 | 0 | 0
Outcome 2 < Insert title > | a | Cost of staff assigned to the project |  |  | 0 |  | Q2 | 0
| b | Travel and subsistence costs for staff and other persons taking part in the project |  |  | 0 |  |  | 0
| c | Purchase costs for equipment (new or used) and supplies |  |  | 0 |  |  | 0
| d | Costs of consumables |  |  | 0 |  |  | 0
| e | Costs of service, supply and work contracts awarded by the requesting organisation |  |  | 0 |  |  | 0
| f | Costs deriving directly from the requirements of the contract |  |  | 0 |  |  | 0
| g | Co-Funding |  |  | 0 |  |  | 0
|  | (Sub)Outcome total | 0 | 0 | 0
Outcome 3 Increasing access to the local labor market < Insert title > | a | Cost of staff assigned to the project |  |  | 0 |  | Q3 | 0
| b | Travel and subsistence costs for staff and other persons taking part in the project |  |  | 0 |  |  | 0
| c | Purchase costs for equipment (new or used) and supplies |  |  | 0 |  |  | 0
| d | Costs of consumables |  |  | 0 |  |  | 0
| e | Costs of service, supply and work contracts awarded by the requesting organisation |  |  | 0 |  |  | 0
| f | Costs deriving directly from the requirements of the contract |  |  | 0 |  |  | 0
| g | Co-Funding |  |  | 0 |  |  | 0
|  | (Sub)Outcome total | 0 | 0 | 0
Outcome 4 < Insert title > | a | Cost of staff assigned to the project |  |  | 0 |  | Q4 | 0
| b | Travel and subsistence costs for staff and other persons taking part in the project |  |  | 0 |  |  | 0
| c | Purchase costs for equipment (new or used) and supplies |  |  | 0 |  |  | 0
| d | Costs of consumables |  |  | 0 |  |  | 0
| e | Costs of service, supply and work contracts awarded by the requesting organisation |  |  | 0 |  |  | 0
| f | Costs deriving directly from the requirements of the contract |  |  | 0 |  |  | 0
| g | Co-Funding |  |  | 0 |  |  | 0
|  | (Sub)Outcome total | 0 | 0 | 0
Total budget |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0%
Applicants are requested to submit their budgets in EUR

## a. Costs of staff (hidden)
EDU-Syria budget proposal | [12 empty] | 0
1
General Project information | Project name: | 0 | [10 empty] | 2
| Project number: | < enter project nr. > | [10 empty] | 3
| Applying organization: | 0 | [10 empty] | 4
| Grant amount: | 0 | [10 empty] | 5
| Project period: | 0 | - | #REF! | [8 empty] | 6
| Project duration (months) | #REF! | [10 empty] | 0
| Reporting quarter | 0
Cost of staff assigned to the project
Costs breakdown
Outcome | Description of costs / reason for payment | Amount in local currency |  | Exchange rate | Amount in EUR = Coloum E/G | Amount Spent in local currency | Exchange rate | Amount spent in EUR | Remaining amount in EUR | Reporting quarter | Date of receipt | Supporting doc. number(s)
Outcome 3: Increasing access to the local labor market | Project Manager (Assigned for 9-months) - 1500 JDS per month |  |  |  | #DIV/0! | 0 | 0 | 0 | #DIV/0!
| Project Coordinator |  |  |  | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0!
| Accountant and Adminstration |  |  |  | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0!
Total |  | 0 |  |  | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0!
Q1
| Project Manager (Assigned for 9-months) - 1500 JDS per month |  |  |  |  | 0 |  |  | 0
0
0
| Project Coordinator |  |  |  |  | 0 |  |  | 0
| Accountant and Adminstration |  |  |  |  | 0 |  |  | 0
0
Total Q1 | [5 empty] | 0
Q2
Project Manager (Assigned for 9-months) - 1500 JDS per month
Project Coordinator
Accountant and Adminstration
Total Q2 | [5 empty] | 0 |  | 0
Q3
Project Manager (Assigned for 9-months) - 1500 JDS per month
Project Coordinator
Accountant and Adminstration
Total Q3 | [5 empty] | 0 |  | 0
Total |  | 0 |  |  | #DIV/0! | 0 |  | 0 | #DIV/0!

## b. Travel and subsistence costs (hidden)
EDU-Syria budget proposal | [8 empty] | 0
1
General Project information | Project name: | 0 | [6 empty] | 2
| Project number: | < enter project nr. > | [6 empty] | 3
| Applying organization: | 0 | [6 empty] | 4
| Grant amount: | 0 | [6 empty] | 5
| Project period: | 0 | - | #REF! |  |  |  |  | 6
| Project duration (months) | #REF! | [6 empty] | 0
| Reporting quarter | 0
Travel and subsistence costs for staff and other persons taking part in the project
Costs breakdown
Outcome | Description of costs / reason for payment | Amount in local currency |  | Exchange rate | Amount in EUR | Amount Spent in local currency | Exchange rate | Amount Spent in EUR | Remaining amount in EUR | Reporting quarter | Date of receipt | Supporting doc. number(s)
| Internships for 40 individuals (Transportation) phase 2 |  |  |  | #DIV/0! | 0 |  | 0 | #DIV/0!
| Training for 17 participants (Transportation) phase 3 (1 MONTH ) |  |  |  | #DIV/0! |  |  | 0 | #DIV/0!
| English training for 17 participant (Transportation) phase 3 ( 1 MONTH ) |  |  |  | #DIV/0! |  |  | 0 | #DIV/0!
| Work in business incubators17 ( transportation) phase 4 ( 1M0NTH ) |  |  |  | #DIV/0!
Total |  | 0 |  |  | #DIV/0! | 0 | 0 | 0 | #DIV/0!
Q2
Internships for 40 individuals (Transportation) phase 2
| Training for 17 participants (Transportation) phase 3 (1 MONTH ) | [6 empty] | 0
| English training for 17 participant (Transportation) phase 3 ( 1 MONTH ) | [6 empty] | 0
| Work in business incubators17 ( transportation) phase 4 ( 1M0NTH ) | [6 empty] | 0
Total Q2 |  | 0 |  |  | 0 | 0 |  | 0
Q3
| Internships for 40 individuals (Transportation) phase 2 |  |  |  |  | 0 |  | 0
Training for 17 participants (Transportation) phase 3 (1 MONTH )
English training for 17 participant (Transportation) phase 3 ( 1 MONTH )
Work in business incubators17 ( transportation) phase 4 ( 1M0NTH )
Total Q3 | [5 empty] | 0 |  | 0
Total |  | 0 |  |  | #DIV/0! | 0 |  | 0 | #DIV/0!

## c. Purchase costs for equipment (hidden)
EDU-Syria budget proposal | [8 empty] | 0
1
General Project information | Project name: | 0 | [6 empty] | 2
| Project number: | < enter project nr. > | [6 empty] | 3
| Applying organization: | 0 | [6 empty] | 4
| Grant amount: | 0 | [6 empty] | 5
| Project period: | 0 | - | #REF! |  |  |  |  | 6
| Project duration (months) | #REF! | [6 empty] | 0
| Reporting quarter | 0
Purchase costs for equipment (new or used) and supplies
Costs breakdown
Outcome | Description of costs / reason for payment | Amount in local currency |  | Exchange rate | Amount in EUR | Amount Spent in local currency | Exchange rate | Amount spent in EUR | Remaining amount in EUR | Reporting quarter | Date of receipt | Supporting doc. number(s)
|  | 0 |  |  | 0 | 0 |  | 0 | 0 | 1
Total |  | 0 |  |  | 0 | 0 | 0 | 0 | 0
Total |  | 0 |  |  | 0
Total |  | 0 |  |  | 0 | 0 |  | 0 | 0

## d. Costs of consumables (hidden)
EDU-Syria budget proposal | [8 empty] | 0
1
General Project information | Project name: | 0 | [6 empty] | 2
| Project number: | < enter project nr. > | [6 empty] | 3
| Applying organization: | 0 | [6 empty] | 4
| Grant amount: | 0 | [6 empty] | 5
| Project period: | 0 | - | #REF! |  |  |  |  | 6
| Project duration (months) | #REF! | [6 empty] | 0
| Reporting quarter | 0
Costs of consumables
Costs breakdown
Outcome | Description of costs / reason for payment | Amount in local currency |  | Exchange rate | Amount in EUR | Amount Spent in local currency | Exchange rate | Amount spent in EUR | Remaining amount in EUR | Reporting quarter | Date of receipt | Supporting doc. number(s)
| Office stationary and supplies for the training / |  |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! | 4 | 1/4/2022 18/05/2022 | 34/01 & 37
Stationery and office supplies for training / graduation supplies
/ certificates
Total |  | 0 |  |  | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0!
Q2
| Office stationary and supplies for the training / | [8 empty] | 2 | Oct.21 | 13
| Stationery and office supplies for training / graduation supplies | [8 empty] | 2 | Nov.18 | 13
/ certificates
Total |  | 0 |  |  | 0
Total |  | 0 |  |  | #DIV/0! | 0 |  | 0 | #DIV/0!

## e. Costs entailed by contracts (hidden)
EDU-Syria budget proposal | [8 empty] | 0
1
General Project information | Project name: | 0 | [6 empty] | 2
| Project number: | < enter project nr. > | [6 empty] | 3
| Applying organization: | 0 | [6 empty] | 4
| Grant amount: | 0 | [6 empty] | 5
| Project period: | 0 | - | #REF! |  |  |  |  | 6
| Project duration (months) | #REF! | [6 empty] | 0
| Reporting quarter | 0
Costs of service, supply and work contracts awarded by the requesting organisation
Costs breakdown
Outcome | Description of costs / reason for payment | Amount in local currency |  | Exchange rate | Amount in EUR | Amount Spent in local currency | Exchange rate | Amount spent in EUR | Remaining amount in EUR | Reporting quarter | Date of receipt | Supporting doc. number(s)
| Software-based training programs for 15 individuals |  |  |  | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0!
| 3 English language courses -1 month capacitor 17 individuals, 226 JD |  |  |  | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0!
| 17 computers/laptops 450 JD price of one laptop |  |  |  | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0!
| Venue rental (20 days) |  |  |  | #DIV/0! | 0 | 0 | 0 | #DIV/0!
Total |  | 0 |  |  | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0!
Q1
| Software-based training programs for 15 individuals |  |  |  |  | 0 |  | 0
| 3 English language courses -1 month capacitor 17 individuals, 226 JD |  |  |  |  | 0 |  | 0
| 17 computers/laptops 450 JD price of one laptop | [6 empty] | 0
Venue rental (20 days)
Total Q1 |  | 0 |  |  | 0 |  |  | 0
Q3
Software-based training programs for 15 individuals
3 English language courses -1 month capacitor 17 individuals, 226 JD
17 computers/laptops 450 JD price of one laptop
Venue rental (20 days)
Total Q3 | [5 empty] | 0 |  | 0
Total |  | 0 |  |  | #DIV/0! | 0 |  | 0 | #DIV/0!

## f. Costs from contract req. (hidden)
EDU-Syria budget proposal | [8 empty] | 0
1
General Project information | Project name: | 0 | [6 empty] | 2
| Project number: | < enter project nr. > | [6 empty] | 3
| Applying organization: | 0 | [6 empty] | 4
| Grant amount: | 0 | [6 empty] | 5
| Project period: | 0 | - | #REF! |  |  |  |  | 6
| Project duration (months) | #REF! | [6 empty] | 0
| Reporting quarter | 0
Costs deriving directly from the requirements of the contract
Costs breakdown
Outcome | Description of costs / reason for payment | Amount in local currency |  | Exchange rate | Amount in EUR | Amount Spent in local currency | Exchange rate | Amount spent in EUR | Remaining amount in EUR | Reporting quarter | Date of receipt | Supporting doc. number(s)
[5 empty] | #DIV/0! | 0 |  | 0 | 0 | 1
Total |  | 0 |  |  | #DIV/0! | 0 | 0 | 0 | 0
Total |  | 0 |  |  | 0
Total |  | 0 |  |  | #DIV/0! | 0 |  | 0 | 0

## g. Co-funding (hidden)
EDU-Syria budget proposal | [8 empty] | 0
1
General Project information | Project name: | 0 | [6 empty] | 2
| Project number: | < enter project nr. > | [6 empty] | 3
| Applying organization: | 0 | [6 empty] | 4
| Grant amount: | 0 | [6 empty] | 5
| Project period: | 0 | - | #REF! |  |  |  |  | 6
| Project duration (months) | #REF! | [6 empty] | 0
| Reporting quarter | 0
Co-Funding
Costs breakdown
Outcome | Description of costs / reason for payment | Amount in local currency |  | Exchange rate | Amount in EUR | Amount Spent in local currency | Exchange rate | Amount spent in EUR | Remaining amount in EUR | Reporting quarter | Date of receipt | Supporting doc. number(s)
|  | 0 |  |  | 0 | 0 |  | 0 | 0 | 1
Total |  | 0 |  |  | 0 | 0 | 0 | 0 | 0
Total |  | 0 |  |  | 0
Total |  | 0 |  |  | 0 | 0 |  | 0 | 0